## Bugs
Technical Services Known Problems (Bugfixes)
Collection Maintenance Subcommittee 1/12/22
Title of problem | Module | Date reported | SCLS Support Ticket number | Notes | User Group Comments | CMS Comments | Priority from User Group
GetIt Acquisitions: Clicking "+" to expand all PO lines or invoice lines doesn't always work | ACQ | 2020-01-31 | 21613 | If you click the "+" symbol in the upper left-hand corner of the main PO or Invoice screen, so all of the PO or Invoice lines will expand, it doesn't work if there are more than say, 20 Invoice lines on the Invoice. If there more than 20 lines (approximately), the Invoice lines at the bottom of the screen do not display. Also, if you are on the main PO screen or Invoice screen, and you click the "+" to expand PO lines or Invoice lines, the full set of PO or Invoice lines may not display if there are more than 15-20 lines to display. | delay in the screen display |  | high
Session defaults are not applied when a new browser tab is opened | CAT | 2020-02-27 | 22210 | The session defaults for item records are not applied when a new browser tab is opened in the same browser. |  |  | high
Records with lots of items take too long to load | CAT | 2020-07-21 | 23232 | Records that have a lot of items take a long time to load, and adding/editing items can take even longer. | pagers didn't really help loading speed drastically |  | high
GetIt Acquisitions: When closing PO tabs from left to right PO info from closed tab displays in open PO tabs | ACQ | 2020-12-03 | 24404 | When you open multiple POs, if you close the PO tab on the left, then the information from that closed PO (the header and PO Lines) will then display in the other PO tabs that are open. You have to close all PO tabs and then re-open them to clear this problem. | Also a problem with Invoices |  | high
Batch Item Edit: Remove Checked Out from list of fields | CAT | 2019-12-04 | 20926 | In the Batch Item Editor, Checked out is in the list of fields available for editing. If you try to "edit" the field, such as by removing the "Checked out" status the system doesn't do anything - e.g. it doesn't check in the item, so it's not corrupting data. However, the field shouldn't be in this list, because you shouldn't be able to "edit" the Checked out field via the batch item editor. |  |  | high?
Editing Item from Item Statuses page | CAT | 2020-09-01 | 23626 | If you edit an item from the Edit Items page on a bib, it will automatically reflect the changes on the page when it is updated (row becomes highlighted and changed, etc.), but if you go to the Item Statuses page, choose Edit on an item from there (it'll take you to the Edit Items page), edit something in the popup and save it, the changes are NOT reflected until you refresh the page. |  |  | medium
Batch Item Edit: Cannot select more than one list for deletion | CAT | 2019-07-09 | 19768 | On the Batch Item Edit Lists screen, you cannot select more than one List at a time. On the screen, it appears that you should be able to select multiple batch jobs, and click the "Delete Selected" button to delete multiple batch jobs at once, but you cannot select more than one list, even if you hold down Ctrl key or the Shift key while selecting Lists. |  |  | low
When viewing the item checkout history from item status page, the wrong title and bib # displays | CAT | 2020-02-04 | 21900 | When you click on the View Checkout History link from the item status page, the correct item barcode is displayed on the screen, but the wrong title, author (if present), and bib number are displayed ( the title that displays is for the Bib # that is next numerically). This is a display problem - the item barcode is correct, and the statistics for the item are correct. |  |  | low
Edit new item pop-up sometimes displays fields in alphabetical order | CAT | 2020-02-20 | 22108 | The fields of the item record are set up to display in a certain order. Fields that are most commonly used display first, with lesser-used fields at the end. However, sometimes, when opening an "Edit new item form" to create a new item record, the item record fields will display in alphabetical order instead of the correct order. |  |  | low
Batch Item Editor: can't see all pages in a list | CAT | 2021-05-26 | 25867 | The Batch Item Editor does not show all pages in a list. |  |  | low