## Sheet1
Date | LIB | Questions, concerns, issues
2022-06-09 | ARP | What does the work flow look like to set and remove the local hold only item status? Is this automated or do libraries have to change each individual item at the end of 60 days? | See Steps for Local Holds document. Libraries need to manually change the items.
2022-06-09 | ARP | Is 60 days a long enough time period to have any meaningful impact for local patrons? | Good for the pilot project. Can re-assess after the pilot. Is there a way to survey the patron reaction to this pilot project? Use the Google form that we had talked about to record reactions.
2022-06-09 | ARP | What are the anticipated next steps after the pilot project? Would adopting local holds only be up to each library or a an SCLS-wide change? | Hard to continue if not all libraries participate. Burden on libraries that don't participate. Survey WI systems that use local holds for new items and ask how their structure works.
2022-06-09 | ARP | How is SCLS or individual libraries tracking or measuring the results of the pilot? How would success (or not) be measured? | We need to start the pilot in order to have data we can compare to pre-pandemic data. Not certain how to measure success. We have a lot of questions but no answers yet.
2022-06-10 | ORE | We would find it helpful to have promotional/informational materials to share with patrons about the pilot to explain why new items are available for local holds only. (Already shared with my cluster rep). It may be helpful to have talking points for staff for shared understanding and consistency. | We are hoping to create marketing/informational materials and Talking Points for staff.
2022-06-10 | ORE | 1. Don't Miss Lists: These lists now include records for items which may only have copies available for local holds only. We've already had a patron encounter this in Linkcat and they were confused why they couldn't place a hold. With more libraries participating, this is likely to happen more often. If all libraries owning a popular & new title are participating in the pilot, patrons will not be able to place holds on these titles using Linkcat until a copy is added to the record that allows local holds. There should be communication with staff on whether they can place holds for patrons in this circumstance (we were told this is ok) and information for patrons as this may mean they can't place a hold on a new item themselves until the 60 day window is over. | Can we exclude item from the Don't Miss list if the only copy is a Local Hold? Long term project - limit when the only item is local hold and allow the title to display if a "regular" item is added to the BIB? Right now titles extraced by date added, not easy to add additional limits. How often would this happen? Discuss ramifications of applying Local Hold status to an item that is the only copy in the system.
2022-06-10 | ORE | What feedback from staff would the workgroup like during the pilot and how should this best be provided? Does the workgroup wish to have any mechanisms for patron feedback? | Google form to accept staff and patron feedback during the pilot.
2022-06-10 | BLV | How do we track when items can be removed from local hold status? | 2 months after adding items to the system is when you would process the local holds and change back to "regular" item type. Can change manually or use batch editor.
2022-06-11 | SUN | At SUN, I think we were picturing having our items for the Local Use pilot interfiled with the regular new books. So the renewals restriction has me scrambling a bit -- do we need to put these items on a special display, and if so what kind of label or sticker will each library be using? I don't think there should be a renewal restriction -- if a patron has the item and there aren't additional holds, I think that patron should be allowed to renew it. Otherwise, I feel like that patron is being penalized for picking up this item as opposed to a regular copy. And if only one local patron gets the item in the 60-day window and then renews it twice, I think that's okay too. I do understand that Lucky Day items aren't renewable--and that's why we have them shelved separately. I do recognize that the workgroup has agreed on the renewals limitation, so I just need some recommendations on how libraries should set up their Local Use collections for the pilot, and I'd like the renewals limitation to be revisited if Local Use becomes permanent. | BER planning to shelve with Lucky Day. Perhaps a different color tape on the spine? ACL Walk-in collection and New books. New items shelf. New books.
2022-06-13 | ORE | After the pilot starts on July 1st, will the MFD items that are currently set as local holds that do not fit the project parameters (i.e. format other than Adult Fiction like DVDs) have the local hold status removed or will their special pilot continue? | MFD is going to continue with what they are doing until a decision is made about the larger project.
2022-06-13 | ORE | How will the mix of regular and local hold items on a bib record impact a patron's ability to renew items? Specifically, if there are local hold items that have a status of available, but all the copies that are being shared are in use and there are some people waiting, will a patron still be able to renew an item if the number of local hold items available exceeds the number of holds? (I understand local holds only copies can't be renewed). | This has not been specifically tested but will have an answer before July 1. As the items in the project are likely in-demand and won't be renewable anyway.