## Slide 1: All Director’s November 16, 2023
Technology and ILS Service Priorities 2024

## Slide 2: ILS
Conduct ILS and Discovery Layer Marketplace Evaluation –Lead Workgroup
  Creates final project plan and timeline
  Develops evaluation process
  Develops preliminary evaluation document which will also be incorporated into the final evaluation
  Selects vendors to participate in demos based on preliminary evaluation
  Assists with planning of demos
  Members attend all demos
  Coordinates site visits and/or phone calls to customer sites
  Compiles final evaluation document to be submitted to the ILS Committee

## Slide 3: ILS
Conduct ILS and Discovery Layer Marketplace Evaluation – Proposed topic areas
  Technology Support (SCLS Staff)
  System Administration (SCLS Staff)
  Discovery Layer (including web support)
  Circulation and Patron
  Holds (Circulation (Staff) and Discovery Layer (Patron)
  Self Check/RFID/Sorters/Gates
  Cataloging
  Acquisitions
  Serials
  Reports
  Database authentication (SCLS Staff)
  Vendor viability (SCLS Staff)

## Slide 4: ILS
Conduct ILS and Discovery Layer Marketplace Evaluation – Topic work Groups
  Identify priorities for topic
  Finalize and approve checklists
  Members attend all demos for their topic
  Members attend site visits (optional)
  Create follow-up questions for vendors
  Create final report for lead workgroup

## Slide 5: ILS
Conduct ILS and Discovery Layer Marketplace Evaluation – Proposed 2 year timeline
  Early 2024 – select Lead Workgroup and topic workgroups, choose Discovery Layers to evaluate, develop checklists, schedule vendor demos
  Virtual ILS vendor demos – before SLP? April/May ; After SLP? September/October
  Summer 2024 – SCLS staff conduct virtual visits with system and technology staff for ILS products ; SCLS staff compare bugs and development wish list against ILS products
  Summer/fall? Virtual Discovery Layer demos?? Fit them in depending on workgroup members schedule?
  Fall/Winter 2024-2025 – virtual site visits ; in person site visits ; follow up from site visits
  Early 2025 – preliminary reports from topic workgroups; final report from Lead Work Group; review by directors; vote (possibly at November All Director’s meeting)
Possible exploration of holds workflow in libraries

## Slide 6: Technology
Continue to increase security measures
  Multi-factor authentication for SCLS provided email accounts (in pilot testing)
  Increase security to LINKcat accounts
    Review ILS Scripting and API Policy
    Review ILS permissions and password policy
    Review ILS policies ( Retention practices of sensitive patron data; assure conformance with Wisconsin data retention policies)
  Password protected Technology website
  Cybersecurity training requirement (infosec)
  Security-related software licenses
  Complete Cyber Incident response plan for SCLS technologies

## Slide 7: Technology
Network
  Leverage network automation platforms to provide low-touch provisioning processes for network deployments
  Explore Next-Generation platforms and design for SCLS core network
  Explore alternative network vendors that are both cost-effective and feature-rich that meet the current/future requirements of SCLS networks (currently piloting Juniper equipment)

## Slide 8: Technology
Software, etc.
  Deploy new version of Microsoft Office
  Replace ESET
Data
  Develop a user-friendly algorithmic method to identify peer libraries based on various sets of criteria

## Slide 9: Increase in Envisionware Maintenance
Purchased by an investment company that won’t allow them to keep maintenance costs frozen
Plan on 5% increase in 2025 (worst case scenario)
Reviewing current maintenance renewal plans for where increases will fall
Requesting no more than 5% increase cap in future quotes / agreements